## Sheet1
No. | Product Deliverables | Task | Lê Phước Việt | Nguyễn Xuân Sơn | Unit | Size
1 | Report1 - Introduction | Report 1 |  | O
|  | Website prototype | O
|  | Identify business of guest |  | O
|  | Identify business of normal user | O
|  | Identify business of administrator |  | O
|  | Identify business of hospital user | O
2 | Report2- Software Project Management Plan | Report 2 |  | O
|  | Website prototype | O
|  | Project management plan | O
|  | Study Boyer Moore algorithm |  | O
|  | Study Geographic Information Retrieval algorithm | O
|  | Study Hunspell for checking grammar | O
|  | Prepare hospitals data |  | O
|  | Prepare speciality data |  | O
|  | Prepare supporting service data |  | O
|  | Prepare facility data |  | O
|  | Prepare Disease data |  | O
3 | Report 3- Software Requirement Specification | Report 3 |  | O
System Requirement Specification
Functional Requirement
|  | System Overview |  | O
|  | <GU> Overview | O
|  | <GU> Login | O
|  | <GU> Search hospital |  | O
|  | <GU> View hospital information | O
|  | <GU> Search doctor | O
|  | <GU> Feedback | O
|  | <NU> Overview |  | O
|  | <NU> Searh hospital |  | O
|  | <NU> View hospital information | O
|  | <NU> Search doctor | O
|  | <NU> Feedback | O
|  | <NU> Comment | O
|  | <NU> Reply comment | O
|  | <NU> Rating hospital | O
|  | <US> Logout | O
|  | <HU> Overview |  | O
|  | <HU> Add new doctor | O
|  | <HU> View list of doctors | O
|  | <HU> Update doctor information | O
|  | <HU> View hospital feedback | O
|  | <HU> Upload photo |  | O
|  | <HU> Update Hospital information |  | O
|  | <HU> View hospital's statistics | O
|  | <HU> Change password | O
|  | <AD> Overview |  | O
|  | <AD> Create hospital user's account |  | O
|  | <AD> View system feedback | O
|  | <AD> View list of users | O
|  | <AD> Activate user | O
|  | <AD> Deactivate user | O
|  | <AD> View system statistics | O
|  | <AD> Import hospital using excel |  | O
|  | <AD> Add hospital |  | O
|  | <AD> Upload photo |  | O
|  | <AD> Display list of hospitals |  | O
|  | <AD> Upldate hospital information |  | O
|  | <AD> Add speciality |  | O
|  | <AD> View list of specialities |  | O
|  | <AD> Update specialities |  | O
|  | <AD> Add facitlity |  | O
|  | <AD> View list of facilities |  | O
|  | <AD> Update facilty |  | O
|  | <AD> Add service |  | O
|  | <AD> View list of services |  | O
|  | <AD> Update service |  | O
|  | Non-functional Requirement |  | O
|  | Entity Relationship Diagram |  | O
4 | Report 4- Software Design Description | System Architectural Design |  | O
|  | Class diagram |  | O
Class specification (states, behaviors)
|  | User |  | O
|  | Hospital |  | O
|  | Hospital Type |  | O
|  | Doctor | O
|  | DoctorSpeciality | O
|  | DoctorHospital | O
|  | Role |  | O
|  | Rating | O
|  | Feedback | O
|  | FeedbackType | O
|  | Facility |  | O
|  | FacilityType |  | O
|  | HospitalFacility |  | O
|  | Service | O
|  | ServiceType | O
|  | HospitalService | O
|  | Photo |  | O
|  | Ward |  | O
|  | District |  | O
|  | City |  | O
|  | Speciality | O
|  | HospitalSpeciality | O
|  | Disease | O
|  | SpecialityDisease | O
|  | Tag | O
|  | TagHospital | O
|  | SearchQuery | O
|  | Component Diagram |  | O
Sequence Diagram
|  | Normal search hospital |  | O
|  | Advanced search hospital | O
|  | Location search hospital | O
|  | Import Hospital using excel |  | O
|  | Save valid excel record |  | O
|  | Create hospital |  | O
|  | View hospital detail | O
|  | Display list of hospitals |  | O
|  | Update hospital information |  | O
|  | Comment | O
|  | View statistics | O
Algorithms
|  | Geographic Information Retrieval |  | O
|  | Haversine fomula | O
5 | Report 5 - Software Implementation and Test Document | Setup Environtment | O
Normal search
|  | Create Geographic Information Retrieval function | O |  |  | 5
|  | Optimize Geographic Information Retrieval function |  | O |  | 5
|  | Implement Hunspel |  | O
|  | Create stored procedure SP_NORMAL_SEARCH_HOSPITAL |  | O |  | 3
|  | Implement normal search |  | O |  | 5
Advanced search
|  | Create stored procedure SP_ADVANCED_SEARCH_HOSPITAL |  | O |  | 2
|  | Binding data from database |  | O |  | 1
|  | Implment advanced search |  | O |  | 3
Location search
|  | Implement Haversine fomula | O |  |  | 5
|  | Create stored procedure SP_LOCATION_SEARCH_HOSPITAL | O |  |  | 5
|  | Implment location search | O |  |  | 3
Display hospital details
|  | Interact Google map | O |  |  | 3
|  | View hospital information | O |  |  | 1
|  | Rating | O |  |  | 1
|  | Comment | O |  |  | 1
|  | View list of hospitals |  | O |  | 1
|  | Add hospital |  | O
|  | Interact Google map |  | O |  | 1
|  | Create hospital user account |  | O |  | 1
|  | Add hospital |  | O |  | 3
|  | Update hospital information |  | O
|  | Interact Google map |  | O |  | 1
|  | Update hospital information |  | O |  | 3
|  | Define Excel template |  | O |  | 2
|  | Import hospital using excel |  | O |  | 3
Manage meta data
|  | Speciality |  | O |  | 1
|  | Disease |  | O |  | 1
|  | Facility |  | O |  | 1
|  | Service |  | O |  | 1
Feedback management
|  | Create feedback | O |  |  | 1
|  | View list of feedback | O |  |  | 1
Manage doctor
|  | Add doctor | O |  |  | 3
|  | Update doctor information | O |  |  | 3
|  | View list of doctor | O |  |  | 1
Manage user
|  | Change password | O |  |  | 1
|  | Forgot password | O |  |  | 1
|  | View list of users | O |  |  | 1
|  | Change user status | O |  |  | 1
Statistics
|  | Hospital statistics | O |  |  | 2
|  | System statistics | O |  |  | 2
Write Test case
|  | Add hospital |  | O
|  | Import hospital using excel |  | O
|  | View list of hospitals |  | O
|  | Search hospitals |  | O
|  | Create hospital user account | O
|  | Search doctor | O
|  | Create feedback | O
|  | Rating hospital | O
|  | Search list of doctor |  | O
|  | Update hospital information | O
Perform Testing
|  | Add hospital | O
|  | Import hospital using excel | O
|  | View list of hospitals | O
|  | Search hospitals | O
|  | Create hospital user account |  | O
|  | Search doctor |  | O
|  | Create feedback |  | O
|  | Rating hospital |  | O
|  | Search list of doctor | O
|  | Update hospital information |  | O
Others Testing
|  | Monkey test | O
|  | Stress test | O
|  | Checklist | O
6 | Report 6 - Software User's Manual | Installation Guide |  | O
User’s Guide
|  | Normal search |  | O
|  | Advanced search |  | O
|  | Location search | O
|  | Search result | O
|  | Login | O
|  | Add hospital |  | O
|  | Import hospital using excel |  | O
|  | View statistics | O
|  | View list of hospitals | O
|  | Update hospital information |  | O
Notes
No. | Function Types | Function Point Size
1 | Insert, Delete, Update, Simple Search, Login, Register, simple function or simple query on one table | 1
2 | Computed functions or joined query | 2
3 | Complex functions or multiple subquery | 3
4 | Constraint process and data integrity | 4
5 | Functions with implementing algorithms | 5