## Project Phases
Phase | Start Date | End Date | Description | Status
1 | 2014-05-19 | 2014-05-26 | Analyze business and investigate technology | Finished
2 | 2014-05-27 | 2014-06-02 | User requirement specification | In progress

## Phase 1
PHASE 1 (05/19/2014 - 05/26/2014)
Task ID | Task | Description | Assigned to | Expected Start Date | Expected End Date | Real Start Date | Real End Date | Status | Comment
P1T1 | Create report 2 | Project management plant (PMP) | Nguyễn Xuân Sơn | 2014-05-23 | 2014-05-23 | 2014-05-23 | 2014-05-23 | Finished
P1T3 | Create and review general use case | Define methods for each role | Dương Thị Hoàng Anh | 2014-05-20 | 2014-05-20 | 2014-05-20 | 2014-05-20 | Finished
P1T4 | Study Facebook API | Deme a project using Facebook API | Dương Thị Hoàng Anh | 2014-05-22 | 2014-05-26 | 2014-05-22 | 2014-05-26 | Finished
Vũ Nhật Anh Khoa
P1T5 | Study responsive website layout | Design layout | Lê Phước Việt | 2014-05-19 | 2014-05-19 | 2014-05-19 | 2014-05-19 | Finished
P1T6 | Create ERD | Create Entity Relation diagram | Nguyễn Xuân Sơn | 2014-05-20 | 2014-05-22 | 2014-05-20 | 2014-05-22 | Finished
P1T7 | Create Physical Database | Create physical database in SQL Server | Nguyễn Xuân Sơn | 2014-05-26 | 2014-05-26 | 2014-05-26 | 2014-05-26 | Finished
P1T8 | Research searching algorithm | Research to find alogorithms for optimizing search method | Lê Phước Việt | 2014-05-21 | 2014-05-26 |  |  | In progress | Still working on optimize algorithm
Nguyễn Xuân Sơn
P1T9 | Study Google API | Research Google API to demo 02 main functions: display one place on map with some brief description and display places that is near to pre-defined place | Lê Phước Việt | 2014-05-22 | 2014-05-26 | 2014-05-22 | 2014-05-26 | Finished
P1T10

## Phase 2
PHASE 2 (05/27/2014 - 06/02/2014)
Task ID | Task | Description | Assigned to | Expected Start Date | Expected End Date | Real Start Date | Real End Date | Status | Comment
P2T1 | Login use case | Describe system login and Facebok login use case | Vũ Nhật Anh Khoa | 2014-05-27 | 2014-05-27 |  |  | In progress
P2T2 | Change password use case | Describe how users can change their password | Vũ Nhật Anh Khoa | 2014-05-27 | 2014-05-27 |  |  | In progress
P2T3 | Reclaim forgot password use case | Describe how users can reclaim their password in case of forgoting | Vũ Nhật Anh Khoa | 2014-05-27 | 2014-05-27 |  |  | In progress
P2T4 | Create hospital users' account use case | In case of creating new user for an existed hospital or clinic, assigned that center for the user. In case of creating new user for new hospital or clinic, a form of creating new hospital is required. | Dương Thị Hoàng Anh | 2014-05-27 | 2014-05-27 |  |  | In progress
P2T5 | Update hospital users's account use case | Update hospital users' accounts | Dương Thị Hoàng Anh | 2014-05-28 | 2014-05-28 |  |  | In progress
P2T6 | Deactivate or activate normal or hospital users' accounts use case | Deactivate or activate users in the system | Dương Thị Hoàng Anh | 2014-05-28 | 2014-05-28 |  |  | In progress
P2T7 | View list of users or hospital users use case | Display a list of users in the system. Support column sort, filter and paging | Vũ Nhật Anh Khoa | 2014-05-28 | 2014-05-28 |  |  | In progress
P2T8 | View hospitals or clinics information use case | Display information about a specific hospital or clinic. Including basic contact address, comments and rating | Vũ Nhật Anh Khoa | 2014-05-28 | 2014-05-28 |  |  | In progress
P2T9 | Update hospitals or clinics information use case | Update information of a specific hospital or clinic | Dương Thị Hoàng Anh | 2014-05-28 | 2014-05-28 |  |  | In progress
P2T10 | Comment use case | Create a new comment about hospitals or clinics | Dương Thị Hoàng Anh | 2014-05-28 | 2014-05-28 |  |  | In progress
P2T11 | Reply comment use case | Reply a comment about a specific hospital or clinic | Dương Thị Hoàng Anh | 2014-05-28 | 2014-05-28 |  |  | In progress
P2T12 | Create feedback use case | Create new feedback about a specfic hospital or clinic, or give contribution for administrators of the system | Vũ Nhật Anh Khoa | 2014-05-28 | 2014-05-28 |  |  | In progress
P2T13 | View list of feedbacks use case | Display a list of feedbacks. Support column sort, filter and paging | Vũ Nhật Anh Khoa | 2014-05-28 | 2014-05-28 |  |  | In progress
P2T14 | Import list of hospitals or clinics by Excel use case | Import a list of hospitals and clinics to the system through a pre-defined Excel template | Vũ Nhật Anh Khoa | 2014-05-28 | 2014-05-28 |  |  | In progress
P2T15 | Rating use case | Rate by score about a specific hospital or clinic. | Dương Thị Hoàng Anh | 2014-05-29 | 2014-05-29 |  |  | In progress
P2T16 | Create appointments online use case | Create a new appoitnment | Dương Thị Hoàng Anh | 2014-05-29 | 2014-05-29 |  |  | In progress
P2T17 | View list of appointments use case | Display a list of appointments through Google calendar | Vũ Nhật Anh Khoa | 2014-05-29 | 2014-05-29 |  |  | In progress
P2T18 | View administrator statistics use case | Statistics about | Vũ Nhật Anh Khoa | 2014-05-29 | 2014-05-29 |  |  | In progress
P2T19 | View hospital statistics use case | Top 10 illness or disease that have the highest search percent by users monthly and annually | Dương Thị Hoàng Anh | 2014-05-29 | 2014-05-29 |  |  | In progress
P2T20 | Review and update use case | Manage monthly appointments or annual appointment | Nguyễn Xuân Sơn | 2014-05-30 | 2014-06-02 |  |  | In progress
Vũ Nhật Anh Khoa
Dương Thị Hoàng Anh
P2T21 | Create report 4 |  | Nguyễn Xuân Sơn | 2014-06-02 | 2014-06-02 |  |  | In progress
P2T22 | Research searching algorithm |  | Lê Phước Việt | 2014-05-27 | 2014-05-30 |  |  | In progress
Nguyễn Xuân Sơn