## Sheet1
HospitalF Project Plan
No. | Task | Description | Assignee | Start Date | Due Date
1 | Research searching algorithm | Research to find out alogorithm for optimize hostpital finding from user's input | SonNX, VietLP | 22/05/2014
2 | Study Facebook API | Try to use facebook API to demo some main functions that faebook provided for developer | AnhDTH, KhoaVNA | 22/05/2014
3 | Design Web Interface | Design one repsonsive web interface that applicable both computer and mobile devices. There are 02 main GUI: User Page and Administrator Page | VietLP | 22/05/2014
4 | Review ERD | Keep on reviewing and editing ERD in order to find out optimize searching algorithms | SonNX, VietLP | 22/05/2014
5 | Review Use Case model | Review and supplement use case | AnhDTH, KhoaVNA | 22/05/2014
6 | Collect data source | Collect and review data source from internet to find out trustworthy data sources | SonNX | 22/05/2014
7 | Study Google API | Try to use Google API to demo 02 main functions: display one place on map with some brief description and display places that is near to pre-defined place |  | 22/05/2014