## Project Phases
Phase | Start Date | End Date | Description | Status
1 | 2014-05-19 | 2014-05-26 | Analyze business and investigate technology | In progress

## Phase 1
PHASE 1 (05/19/2014 - 05/26/2014)
Task ID | Task | Description | Assigned to | Start Date | End Date | Status | Comment
P1T1 | Create report 2 | Project management plant (PMP) | Lê Phước Việt |  |  | In progress
P1T2 | Review report 2 | Project management plant (PMP) | Nguyễn Xuân Sơn |  |  | In progress
P1T3 | Create and review general use case | Define methods for each role | Dương Thị Hoàng Anh | 2014-05-20 | 2014-05-20 | Finished
P1T4 | Study Facebook API | Deme a project using Facebook API | Dương Thị Hoàng Anh |  |  | In progress
Vũ Nhật Anh Khoa
P1T5 | Create website interface | Design layout | Lê Phước Việt |  |  | In progress
P1T6 | Create ERD | Create Entity Relation diagram | Nguyễn Xuân Sơn | 2014-05-20 | 2014-05-22 | Finished
P1T7 | Create Physical Database | Create physical database in SQL Server | Nguyễn Xuân Sơn |  |  | In progress
P1T8 | Research searching algorithm | Research to find alogorithm for optimizing search method | Lê Phước Việt |  |  | In progress
Nguyễn Xuân Sơn
P1T9 | Study Google API | Research Google API to demo 02 main functions: display one place on map with some brief description and display places that is near to pre-defined place | Lê Phước Việt |  |  | In progress
P1T10
P1T11
P1T12
P1T13
P1T14
P1T15
P1T16
P1T17
P1T18
P1T19
P1T20
P1T21
P1T22
P1T23
P1T24
P1T25
P1T26
P1T27
P1T28
P1T29
P1T30
P1T31
P1T32
P1T33
P1T34
P1T35
P1T36
P1T37
P1T38
P1T39
P1T40
P1T41
P1T42
P1T43
P1T44
P1T45
P1T46
P1T47
P1T48
P1T49
P1T50
P1T51
P1T52
P1T53
P1T54